## Dashboard
Legendary Horizon Completion Tracker v1
Created 2026-06-09 — operational tracker for next Claude coding session
# | Work Item | Cluster | Priority | Required Outcome | Backlog Count
1 | Environment parity / build stamp | Critical Infrastructure | Do first | Make local dev, local production preview, and GitHub Pages comparable. Add in-game build/debug stamp and pre-deploy checklist. | 30
2 | Acts I-II save/load integrity | Demo/Classroom Blocker | Do first | Fix Scroll of Destiny reload: Foretold Signposts, prophecy, burned-in sigil, reflection archive states.
3 | Document input + Quest of Fate quality pass | Classroom Blocker | Next | Confirm keys work in document fields while Phaser ignores controls. Make Quest of Fate complete, scrollable, student-ready.
4 | Knowledge combat content + SFX + failure testing | Core System | Next | Fix launch SFX, add question bank/no-repeat logic, test knowledge failure and physical combat failure.
5 | Aethelwood renderer verification | Regression Verification | Next | Verify crops visible, windmill animated, Oracle altar visible on Chromebook/GitHub build.
6 | Act III Guild Hub expansion plan | Next Milestone | After blockers | Add entry gates for every placed Guild HQ and prove hub entry, fog clearing, save/load persistence, and Act IV bridge.

## Clusters
Cluster | Scope | Status | Next Action
Environment Parity / Deployment Reliability | Local Vite, local production preview, GitHub Pages, school Chromebook must be distinguishable and comparable. | Open | Add build stamp; audit base paths/assets/env flags/cache; establish test labels.
Acts I-II State Persistence | Scroll of Destiny, prophecy, signposts, sigil, reflection archive, quest state after Load Game. | Open / High Priority | Audit save payload and hydration paths. Fix temporary React-only state.
Scroll / Oracle / Sigil Moment | Scroll reveal, Foretold Signposts, Oracle sequence, transparent sigil, burn-in, permanent hub state. | Partially Implemented | Verify y-position, transparency asset, burn-in persistence, no skip behavior.
Dialogue Presentation and Accessibility | NPC portraits/busts, narration tracks, dialogue history archive, replay/read-aloud. | Not Started / Designed | Add dialogue metadata model with optional audio asset id and Field Journal replay UI.
Classroom Document System | Quest of Fate, Work Files, submission to teacher, polished student documents. | Open | First: Quest of Fate completeness and scrollable layout; then submit-to-teacher workflow.
Field Journal / Quest Log / Records | Main/side quest toggles; Journey Review, Field Notes, Enemy Records, Realm Notes, Reflection Archive. | Open | Define non-overlapping categories and implement Main Quest/Side Quest quick fix.
Aethelwood / Tiled Rendering | Crops, windmill animation, Oracle passive object, map asset paths. | Needs Test | Verify recent renderer fixes on local preview and GitHub/Chromebook.
Combat Health / Failure / Overwhelmed | Resolve/HP visuals, knowledge and physical combat failure, no-death retreat to camp. | Open | Test failure cases and build consistent Resolve UI/damage feedback.
Knowledge Combat Question System | Question bank, no-repeat cycling, prompt/answer/explanation metadata, SFX routing. | Open | Implement structured bank and session-used question tracking.
Act III Guild Hub Expansion | Entrance triggers for every placed Guild HQ; hub modules; fog clearing; Act IV unlock. | Not Started | Start after environment and Act I-II state blockers.
Inventory / Rewards / Economy | Consumables, collectibles, drops, quest rewards, Guild HQ weapons/spells, item audit. | Not Implemented Permanently | Convert audit into item registry and save-backed inventory plan.
Sprite / Animation Production Pipeline | New Traveler sprite, 8-direction states, walking, weapons, spells, item effects. | In Progress Outside Code | Continue Pixel Lab/Aseprite workflow and define export naming conventions.
Act IV-V Narrative / Document / NPC Work | Guild Manager NPCs, job application, Trial of Tongues, soft skills, final presentation/transcription. | Future Core Work | Build after Act III gates prove the main loop.

## Backlog
ID | Cluster | Item | Priority | Status | Definition of Done / Notes
B-001 | Environment Parity | Add in-game build/debug stamp | Critical | Open | Show commit/build id, build date, env mode, asset base path, save mode, map JSON, backend mode.
B-002 | Environment Parity | Local production preview workflow | Critical | Open | Document npm build + preview test before GitHub deploy; do not count local dev as GitHub verified.
B-003 | Save/Load | Scroll complete after Load Game | Critical | Open | Reload must show signposts/runes, prophecy, and burned-in sigil.
B-004 | Save/Load | Reflection Archive data after Load Game | Critical | Open | Clarify awaiting teacher review vs missing data; bind real save/reflection fields.
B-005 | Input/Documents | Document typing ownership | Critical | Needs Test | All keys work in documents; Phaser ignores gameplay controls while overlay is open.
B-006 | Documents | Quest of Fate full content/layout pass | Critical | Open | Student-ready scrollable document with full required content, polished like class handout/PDF.
B-007 | Documents | Submit Quest of Fate to teacher | Important | Not Started | Design Apps Script/sheet/dashboard flow before implementation.
B-008 | Scroll/Oracle | Transparent prophecy sigil asset | Important | Open | Replace white square image with true transparent PNG; CSS blend is temporary only.
B-009 | Scroll/Oracle | Burned-in sigil persists on permanent hub | Critical | Open | Same placement after Oracle sequence and after load; no banner-style sigil.
B-010 | Scroll/Oracle | Foretold Signposts banner y-position | Important | Needs Test | Verify after y=504 correction; banner untouched by sigil.
B-011 | Scroll/Oracle | Scroll unfurl animation and SFX stub | Polish | Not Started | Wipe-right/unroll animation with reduced motion support.
B-012 | Aethelwood | Crops visible in gameplay | Important | Needs Test | Verify depth fix on local preview/GitHub/Chromebook.
B-013 | Aethelwood | Windmill animated | Important | Needs Test | Verify object-layer sprite animation fix before/after Research Hub.
B-014 | Aethelwood | Oracle altar visual renders | Important | Needs Test | Verify Atlas-props-mountain exact file/casing and passive scenery render path.
B-015 | Combat | Knowledge battle launch SFX | Important | Open | Enter/start battle must use interact/transition SFX, not attack SFX.
B-016 | Combat | Knowledge question bank and no-repeat cycle | Critical | Open | Structured questions by id/act/quest/realm; avoid repeats until pool exhausted.
B-017 | Combat | Resolve/HP UI and damage feedback | Critical | Open | Visible consistent state for knowledge and physical combat.
B-018 | Combat | Overwhelmed retreat failure test | Critical | Open | No death language; retreat to prior camp after combat failure.
B-019 | Dialogue | NPC bust/headshot beside dialogue | Important | Not Started | Static portrait convention for Scribe, Oracle, Guild Managers.
B-020 | Dialogue | Narration audio stubs | Accessibility | Not Started | Scribe/Oracle audio asset ids; missing audio fails gracefully.
B-021 | Dialogue | Dialogue replay archive | Accessibility | Not Started | Field Journal section with clickable prior NPC dialogue and replay audio.
B-022 | Quest Log | Main Quest / Side Quest toggle buttons | Important | Not Started | Quick reliable category view before full redesign.
B-023 | Field Journal | Define category boundaries | Important | Open | Field Notes vs Journey Review vs Enemy Records vs Realm Notes vs Work Files.
B-024 | Act III | Guild Hub entrance triggers for placed HQs | Critical Next Milestone | Not Started | Each placed HQ enters correct hub/research module.
B-025 | Act III | Fog clearing across all guild hubs | Critical Next Milestone | Not Started | Map can fully clear and persist; bridge toward Act IV.
B-026 | Inventory | Permanent item registry/inventory plan | Important Later | Not Started | Convert audit/economy concepts to save-backed implementation.
B-027 | Inventory | Enemy drops / rewards / consumables | Important Later | Not Started | Tie combat and guild unlocks to items, weapons/spells, collectibles.
B-028 | Sprite Pipeline | Traveler Pixel Lab/Aseprite export workflow | Important Later | In Progress | 8-direction idle/walk, transparency, future weapons/spells/effects.
B-029 | Act IV-V | Guild Manager NPC/dialogue/document sequencing | Future Core | Not Started | Build like Act I-II: timed moments, portraits, documents, trials.
B-030 | Verification | Session-end Claude protocol | Critical Process | Open | Every session ends with files changed, commits, completed/open items, test checklist.

## Test Checklist
# | Checklist Item
1 | Clean git status before testing/deploying.
2 | Record current commit/build id and confirm in-game build stamp.
3 | Run local dev only for fast iteration; do not mark as final.
4 | Run production build and local preview before GitHub deploy.
5 | Verify assets load: scroll, sigil, map JSON, tilesets, audio stubs.
6 | Run Start Game → Intro → Scribe prompt → battle → Scroll reveal → Oracle → Fireside save → Load.
7 | After Load, inspect Scroll of Destiny, Reflection Archive, quest state, and map state.
8 | Run Aethelwood test: crops, windmill animation, Research Hub, fog reveal, return to exploration.
9 | Run document test: Quest of Fate typing keys + no Phaser control bleed.
10 | End Claude session with files changed, commits, status updates, remaining risks, next test checklist.

## Claude Prompt
Recommended Next Claude Prompt
NEXT CLAUDE SESSION MISSION Treat this as a stabilization and verification session before adding new story content. 1. Add Environment Parity / Deployment Reliability support first: - in-game build/debug stamp with commit/build id, build date, environment mode, asset base path, save mode, map JSON, backend mode; - local production preview workflow and pre-deploy checklist; - audit root-relative asset paths, env flags, cache/service worker behavior, and files that exist locally but are not committed. 2. Fix Acts I-II save/load integrity: - Scroll of Destiny must retain Foretold Signpost runes, prophecy text, and burned-in sigil after Load Game; - Reflection Archive must read real save/reflection data or show clear awaiting-review states. 3. Verify recent renderer/input fixes: - document typing keys work normally while Phaser ignores gameplay controls; - crops render in Aethelwood; - windmill animates before and after Research Hub; - Oracle altar visual renders as passive scenery. 4. Do not start Act III expansion until the above are either fixed or explicitly marked deferred. End response with: root causes, files changed, commit hash, tracker status updates, and Chromebook/GitHub test checklist.